Topic: AIPRD

Question 115

Outcome 2: Output 2.1

Senator Evans asked in writing:

ANAO report No 50, 2005-2006

“Arrangements to Manage and Account for Aid Funds Provided Under the Australia-Indonesia Partnership for Reconstruction and Development” (AIPRD)

a. Please provide a status report on actions against the recommendations (agreed by AusAID) of the above report.

b. Please supply details of programs in development, new programs aimed to address the AIPRD initiative, existing programs that will be rolled into the initiative and the value of all these programs since 2005-2006

Answer

- A status report against all of the ANAO report’s recommendations is set out below.

| Recommendation | Status |
| --- | --- |
| 1. The ANAO recommends that AusAID review, at regular intervals, AIPRD programming funding commitments, to ensure they remain appropriate as implementation proceeds. This will be particularly valuable for those programmes where limited information was available at the time of the original commitment. | Ongoing |
| 2. The ANAO recommends that the AIPRD Secretariat regularly brief the Secretaries’ Committee of variations to overall AIPRD expenditure estimates, and the reasons for those variations. | Ongoing |
| 3. The ANAO recommends that AusAID facilitate transparency and accountability in procurement of goods and services by centrally monitoring and reporting to senior management the incidence of, and rationale for, direct sourcing. | Under development |
| 4. The ANAO recommends that AusAID establish systems to reliably report on contract procurement in AusTender. | Under development |
| 5. The ANAO recommends that AusAID monitor/benchmark the cost of AIPRD works and outcomes for the Eastern Indonesia National Road Improvement Project against those obtained through the International Competitive Bidding approach, used by the World Bank for National Roads Improvement Project. This will complement AusAID’s general monitoring of bid competitiveness (requested by the Australian Government), and help inform Australia’s consideration of future eligibility. | Ongoing |
| 6. The ANAO recommends that AusAID enhance AIPRD accountability and transparency by ensuring that the future public reporting on the AIPRD identify and, subsequently, report against: - the expected yearly disbursement of loan and grant funds, by major grant and loan activity; - significant activity milestones; - performance indicators, covering effectiveness, quality and quantity, particularly for larger activities. | Ongoing |
| 7. The ANAO recommends that AusAID include targets, benchmarks or activity levels in performance indicators for the AIPRD, where possible, to enable future results to be interpreted against expectations. This will help strengthen transparency and accountability to the Parliament and stakeholders. | Under development |

b. All of the $1 billion in AIPRD funds has been allocated to high priority reconstruction and development activities by Joint Commission Ministers.  These allocations comprise:

| Amount allocated AUD ($) million | Type of assistance |
| --- | --- |
| Up to $328 million | Eastern Indonesia National Roads Improvement Project |
| Up to $300 million | Basic Education Program |
| Up to $181 million | Aceh Relief, Rehabilitation and Reconstruction Programs |
| Up to $78 million | Australian Partnership Scholarships |
| Up to $50 million Up to $38 million | Government Partnerships Fund Small-Holder Agribusiness Development Program |
| Up to $30 million | Yogyakarta Reconstruction Program |
| Up to $10 million | Disaster preparedness and response |
| UP to $5 million | Response to other disasters outside of Aceh (eg. Nias, Alor) |

Question 18: Attachment A

| 1608512 | Institutional and Governance Advisor | Cardno ACIL Pty Ltd | 26 June 2006 - 29 June 2007 | $417,928.00 | Following the October 2005 earthquake, Australia provided $74 million for immediate and post earthquake assistance to Pakistan. $40 million of this assistance was for post-earthquake reconstruction of schools and health facilities, channelled through the Asian Development Bank (ADB) and UNICEF. A proportion of this amount will support the provision of Australian technical assistance to the reconstruction effort. AusAID has funded the 12 month appointment of an Australian Institutional and Governance Advisor to work with the ADB, in support of the governance component of ADB’s Earthquake Emergency Assistance Project. The advisor is assisting the Government of Pakistan to fast track the establishment of reconstruction agencies and build their capacity to manage post-earthquake reconstruction and recovery. At ADB’s request, AusAID is considering extending the advisor’s input for a further six months to December 2007. |
| --- | --- | --- | --- | --- | --- |
| 1613726 | RAMSI Public Affairs Officer Service Order | GRM International Pty Ltd | 2 August 2006 - 30 November 2007 | $315,762.00 | The Regional Assistance Mission to Solomon Islands (RAMSI) Public Affairs Unit aims to enhance knowledge of and support for RAMSI programs and processes. The RAMSI Public Affairs Officer provides communications support to the RAMSI Development Coordinator and other RAMSI personnel. The Public Affairs Officer’s tasks include media liaison, public diplomacy, advocacy and other public affairs related tasks aimed at enhancing the effectiveness of the aid program. This service order includes costs relating to competitive recruitment, salary and support. |
| 1623074 | Deployee Services Period Offer PNG: ECP – SNS -AusAID | Coffey International Development | 10 August 2006 - 10 May 2007 | $10,410,893.00 | - The deployment of Government and Non-Government Officials is a new form of aid, undertaken by AusAID, to assist in the economic and social development of countries in the Asia Pacific regions. - Under the deployee services contract, the Contractor is required to provide some or all of the following Services as tasked: Security and Occupational Health and Safety (OH&S); Mobilisation; Relief and Work-Related Travel; Residential Accommodation; Office Property/Space; Communications; IT Services; Office Equipment; Vehicles for Deployees; Liaison with Host Organisation; Demobilisation; Services for Short-Term and Emergency Deployments; Recruitment; and Other Ad Hoc Services. - Up to 77 households are covered including officials deployed under the Enhanced Cooperation Program; the Sub-national Strategy and some selected AusAID staff co-located in PNG Government departments and provinces. |
| 1625858 | Interim RAMSI Security Services | DDW Consulting Pty Ltd | 11 September 2006 - 30 April 2007 | $450,000.00 | The contract provides interim Regional Assistance Mission to Solomon Islands (RAMSI) security services to meet the duty of care obligation to RAMSI civilians by reducing their level of security risk. The contractor ensures effective and timely identification and assessment of threats and risks, develops and implements effective security strategies and monitors the implementation of security measures. |
| 1633086 | Interim CTA position | Kellogg Brown & Root Pty Ltd | 10 October 2006 - 10 March 2007 | $355,368.00 | Provision of Technical Assistance (TA) aims to increase the Ministry of Agriculture and Rural Development’s effectiveness implementing Natural Disaster Risk Management Project (NDRMP) and, in accordance with the Natural Disaster Mitigation Partnership objectives, to support a conceptual shift from one focussed on disaster response to integrated disaster risk management (IDRM). The TA will promote and encourage IDRM applications as an appropriate and effective natural disaster management approach, and to demonstrate the benefits through provincial applications as sub-projects of NDRMP. The interim CTA is provided as an interim solution before a longer term TA could be mobilised in country. |
| 1633108 | Leadership Code Commission Investigations Manager | GRM International Pty Ltd | 28 August 2006 - 30 September 2009 | $1,862,378.00 | The Regional Assistance Mission to Solomon Islands (RAMSI) Accountability Program began in January 2005 with provision of technical assistance to all three accountability institutions: the Auditor-General; the Leadership Code Commission (LCC); and the Ombudsman. An investigations management adviser was appointed to work with the LCC to develop investigative and strategic enforcement capacity. The key outcomes from this appointment include: development of robust investigative capacity within the LCC; implementation of the Chairman’s investigation priorities; training and liaison with regional expertise; adoption of a strategic plan which establishes business priorities and maximises the impact of existing resources; establishment and effective functioning of appropriate management processes and systems including the Register of Leader’s Interests (TROLI); and enhanced cooperation between the LCC and the Ombudsman’s office, the Auditor-General’s office, the Public Service Commission, the Parliament and other relevant organisations. |
| 1633109 | Ombudsman’s Office Investigations Manager | GRM International Pty Ltd | 8 September 2006 - 30 September 2009 | $1,869,278.00 | The Regional Assistance Mission to Solomon Islands (RAMSI) Accountability Program began in January 2005 with provision of technical assistance to all three accountability institutions: the Auditor-General; the Leadership Code Commission; and the Ombudsman. Following a request from the Ombudsman, an Investigations Management Adviser was appointed to support the investigative functions of the Office of the Ombudsman. The key outcomes expected of the investigation management adviser are: significant reduction in the case backlog; the identification and follow-up of systemic issues emerging from the complaints caseload; enhanced institutional coordination with the other accountability institutions, Public Service Department, Public Service Commission and other relevant SIG authorities; an effective intake process for facilitation of complaints by ordinary citizens, especially in the provinces; a strategic plan to include capacity building, case management, legislative reform and institutional cooperation; and; enhanced capacity and skills of investigators. |

| Australia's Official Development Assistance (ODA) |  |  |  |  | Question 25: Attachment B |  |
| --- | --- | --- | --- | --- | --- | --- |
| Water and Sanitation, Health and Education Sectors 2005-06 |  |  |  |  |  |  |
| Country | DAC Sector | DAC Sector Description | Department | Activity Number | Activity Name | Total |
| Water and Sanitation 2005/06 expenses (provisional) |  |  |  |  |  |  |
| BANGLADESH | 14030 | Basic health care | AusAid | 006S01 | Arsenic Mitigation Program | 278,567.00 |
| BANGLADESH Total |  |  |  |  |  | 278,567.00 |
| CAMBODIA | 14081 | Education and training in water supply and sanitation | AusAid | 06A243 | IDE Ceramic Water Purifier Rollout Phase 1 | 261,996.15 |
| CAMBODIA Total |  |  |  |  |  | 261,996.15 |
| CHINA | 14010 | Water Resource Policy & Administrative Management | Other Gov Dept | G05620 | Regional impacts of revegetation on water resources of the Loess Plateau | 68,736.00 |
|  |  | Water resources policy and administrative management | AusAid | 06A628 | China Water Entitlements and Trading Activity | 896,750.00 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A00120 | Improving water allocation and management in Yellow River basin | 102,246.00 |
|  |  |  |  | A01001 | Main system water management - Zhanghe Irrigation scheme | 0.00 |
|  |  |  |  | A03075 | LWR1/2002/113 | 151,323.00 |
|  |  |  |  | A03076 | LWR/2002/094 | 187,617.00 |
|  |  |  |  | A03161 | LWR/2003/040 | 0.00 |
|  |  |  |  | A96164 | ACIAR-Water & nitrogen mgmt to increase | 0.00 |
|  |  |  |  | G05621 | Application of innovative irrigated cropping ad soil filtration technology for wastewater | 118,714.00 |
|  | 41050 | Flood prevention/control | AusAid | 997K02 | Yangtze Flood Control and Management | 557,522.47 |
|  |  |  |  | 927G08 | Small Activities Scheme (SAS) | 1,058,421.43 |
| CHINA Total |  |  |  |  |  | 3,141,329.90 |
| COOK ISLANDS | 14010 | Water resources policy and administrative management | AusAid | 038K04 | Water Supply Investigations 2003 | 294,939.62 |
| COOK ISLANDS Total |  |  |  |  |  | 294,939.62 |
| FAR EAST ASIA UNSPECIFIED | 14010 | Water resources policy and administrative management | AusAid | 007K0X | MRC App Hydrological Network Improvement | 513,423.55 |
|  | 14040 | River development | AusAid | 007K2G | MRC Basin Development Planning | 13,334.56 |
| FAR EAST ASIA UNSPECIFIED Total |  |  |  |  |  | 526,758.11 |
| GLOBAL UNSPECIFIED | 14050 | Waste management/disposal | Other Gov Dept | G03293 | Contribution of $30,000 to the Basel Convention on the control of transboundary movements of hazardous wastes and their disposal, voluntary trust fund for developing countries in need of technical assistance. | 0.00 |
|  | 14081 | Education and training in water supply and sanitation | AusAid | 049C07 | Water Quality Initiative | 2,002,337.78 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A99164 | International Water Management Institute | 887,293.02 |
| GLOBAL UNSPECIFIED Total |  |  |  |  |  | 2,889,630.80 |
| INDIA | 14010 | Water resources policy and administrative management | AusAid | 006K01 | Gangtok-Shillong & South Asia Reg. WSP | 2,631,616.92 |
|  | 14030 | Basic drinking water supply and basic sanitation | AusAid | 006K01 | Gangtok-Shillong & South Asia Reg. WSP | 278,053.80 |
|  |  |  |  | 06A258 | Independent Completion Reports | 77,459.00 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A00089 | Permanent beds for irrigated rice-wheat and alternative cropping systems | 336,173.00 |
|  |  |  |  | A01014 | Improving water resource management in India's agriculture | 61,901.00 |
|  |  |  |  | A03212 | SMCN/2002/101 | 0.00 |
| INDIA Total |  |  |  |  |  | 3,385,203.71 |
| INDONESIA | 14010 | Water Resource Policy & Administrative Management | Other Gov Dept | G05456 | The impact of changing agroforestry mosaics on catchment water yield and quality in South-East Asia | 1,811.00 |
|  |  |  |  | G05619 | The impact on changing ecoforestry mosaics on catchment water yield | 1,811.00 |
|  |  | Water resources policy and administrative management | AusAid | 977K1G | WASPOLA (Phase 1&2) | 2,169,125.65 |
|  | 14030 | Basic drinking water supply and basic sanitation | AusAid | 06A081 | KASIH Partnership project design mission | 368,019.50 |
|  |  |  |  | 06A559 | Temporary Housing Assistance | 198,098.00 |
|  | 31140 | Agricultural water resources | AusAid | 057K12 | AIPRD Aceh Aquaculture Rehabilitation Program | 31,715.00 |
| INDONESIA Total |  |  |  |  |  | 2,770,580.15 |
| OCEANIA UNSPECIFIED | 14030 | Basic drinking water supply and basic sanitation | AusAid | 05A029 | Regional Meteorology Support | 70,843.31 |
|  |  |  | Other Gov Dept | G04044 | Pacific regional branch of the International Council on Archives (PARBICA) | 0.00 |
| OCEANIA UNSPECIFIED Total |  |  |  |  |  | 70,843.31 |
| PAKISTAN | 31140 | Agricultural water resources | Other Gov Dept | A05385 | SMCN/2005/144 | 0.00 |
| PAKISTAN Total |  |  |  |  |  | 0.00 |
| PAPUA NEW GUINEA | 14020 | Water supply and sanitation - large systems | AusAid | 008K06 | Lae City Water Supply Project | 144,366.00 |
| PAPUA NEW GUINEA Total |  |  |  |  |  | 144,366.00 |
| PHILIPPINES | 14010 | Water resources policy and administrative management | AusAid | 987R0C | WSS Performance Enhancement Project | 19,565.13 |
|  | 14015 | Water Resources Protection | Other Gov Dept | G05615 | Minimising the Off-site Impact of Pesticides from Agricultural Systems | 11,365.00 |
|  |  |  |  | G05658 | Lake Laguna watershed protection project | 7,849.00 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A03074 | LWR1/2003/006 | 95,076.00 |
|  |  |  |  | A03260 | LWR/2004/069 | 109,692.00 |
|  |  |  |  | A05424 | LWR/2005/060 | 0.00 |
|  |  |  |  | G05622 | Enhancing agricultural production by use of shallow groundwater | 84,391.00 |
| PHILIPPINES Total |  |  |  |  |  | 327,938.13 |
| SOUTH & CENTRAL ASIA UNSPECIFIED | 14015 | Water Resources Protection | Other Gov Dept | G05678 | SMCN/2005/0529 - Modelling raised beds | 7,439.00 |
|  | 14030 | Basic drinking water supply and basic sanitation | AusAid | 006S01 | Arsenic Mitigation Program | -174,665.68 |
| SOUTH & CENTRAL ASIA UNSPECIFIED Total |  |  |  |  |  | -167,226.68 |
| SRI LANKA | 14050 | Waste management/disposal | AusAid | 966K05 | Hikkaduwa Sewage and Waste Management Project | 758,441.43 |
| SRI LANKA Total |  |  |  |  |  | 758,441.43 |
| THAILAND | 14010 | Water Resource Policy & Administrative Management | Other Gov Dept | G05456 | The impact of changing agroforestry mosaics on catchment water yield and quality in South-East Asia | 1,812.00 |
|  |  |  |  | G05619 | The impact on changing ecoforestry mosaics on catchment water yield | 1,812.00 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A01095 | Integrated Water Resource Management | 0.00 |
| THAILAND Total |  |  |  |  |  | 3,624.00 |
| TIMOR-LESTE | 14010 | Water resources policy and administrative management | AusAid | 047K0G | Rural Water Supply and Sanitation | 35,746.42 |
|  | 14020 | Water supply and sanitation - large systems | AusAid | 007K20 | Community Water Supply & Sanitation Program | 1,152,039.21 |
|  | 14030 | Basic drinking water supply and basic sanitation | AusAid | 007K20 | Community Water Supply & Sanitation Program | 1,973,240.18 |
|  |  |  |  | 047K0G | Rural Water Supply and Sanitation | 17,723.40 |
| TIMOR-LESTE Total |  |  |  |  |  | 3,178,749.21 |
| TONGA | 14030 | Basic drinking water supply and basic sanitation | AusAid | 898G12 | Ha'apai Development Fund | 18,311.65 |
|  |  |  |  | 898G13 | Tonga-Australia Community Assistance Scheme | 38,141.01 |
|  | 14050 | Waste management/disposal | AusAid | 018K0T | Solid Waste Management Facility | 2,199,475.18 |
| TONGA Total |  |  |  |  |  | 2,255,927.84 |
| VIET NAM | 14010 | Water resources policy and administrative management | AusAid | 047K0E | RWSS Joint Donor Review and Design | 47,532.32 |
|  |  |  |  | 987G04 | Rural Development Programming | 119,213.88 |
|  | 14020 | Water supply and sanitation - large systems | AusAid | 967R05 | Danang URENCO Sanitation Project | 103,078.45 |
|  |  |  |  | 997K12 | 3 Delta Towns Water Supply & Sanitation | 7,417,934.18 |
|  |  |  |  | 997K1E | Cuu Long Delta RWSS | 3,845,331.22 |
|  | 14030 | Basic drinking water supply and basic sanitation | Other Gov Dept | G04448 | Australian Veterans' Vietnam Reconstruction Group | 0.00 |
|  | 31140 | Agricultural water resources | Other Gov Dept | A03084 | ADP/2002/015 | 133,247.00 |
|  |  |  |  | A98034 | System-wide water management in publicit | 0.00 |
|  | 41050 | Flood prevention/control | AusAid | 007K2I | North Vam Nao Water Control Project II | 4,165,223.11 |
| VIET NAM Total |  |  |  |  |  | 15,831,560.16 |
| Grand Total |  |  |  |  |  | 35,953,228.84 |
| Health 2005/06 expenses (provisional) |  |  |  |  |  |  |
| AFGHANISTAN | 12220 | Basic health care | AusAid | 056101 | Afghan Red Crescent Health Program 2005 | 745,707.26 |
| AFGHANISTAN Total |  |  |  |  |  | 745,707.26 |
| BHUTAN | 12281 | Health personnel development | Other Gov Dept | G04228 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
| BHUTAN Total |  |  |  |  |  | 0.00 |
| BOTSWANA | 13040 | STD control including HIV/AIDS | AusAid | 030C04 | DoHA Outposted HIV/AIDS professional | 61,904.61 |
| BOTSWANA Total |  |  |  |  |  | 61,904.61 |
| CAMBODIA | 12191 | Medical services | AusAid | 047K0B | Landmine Victim Assistance Fund | 149.09 |
|  | 12250 | Infectious disease control | AusAid | 06A051 | Contribution to UNICEF CREATE! project | 510,000.00 |
|  |  |  |  | 06A052 | Contribution to WHO trust fund | 250,000.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 037K08 | HIV/AIDS Anti-Retroviral Therapy | 178,401.42 |
| CAMBODIA Total |  |  |  |  |  | 938,550.51 |
| CHINA | 12110 | Health Policy & Administrative Management | Other Gov Dept | G05473 | Renewal of MOU with Zhejiang Provincial Economic and Trade Commission (ZPETC) | 10,157.02 |
|  |  | Health policy and administrative management | AusAid | 06A298 | China Health Reform Roundtable Series 2006 | 50,000.00 |
|  |  |  |  | 997K1A | Xianyang Integrated Rural Health Service | 1,679,449.57 |
|  | 12220 | Basic health care | AusAid | 007K06 | Tibet Health Sector Support Program | 2,512,771.28 |
|  |  |  |  | 997K05 | Bazhong Rural Health Improvement | 2,121,587.31 |
|  |  |  |  | 997K1A | Xianyang Integrated Rural Health Service | 597,448.82 |
|  | 12250 | Infectious disease control | AusAid | 06A205 | Epidemiologist Placement - China | 247,763.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04158 | Study of HPV 6 l1 virus like particles as a therapeutic vaccine for genital warts and recurrent respiratory papillomatosis | 123,122.00 |
|  |  |  |  | G04162 | Pathways to improved, sustainable morbidity control and prevention of schistosomiasis in the People's Republic of China | 265,942.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 057M04 | China HIV/AIDS Roadmap Technical Support | 1,900,000.00 |
|  |  |  |  | 997K1C | Xinjiang HIV/AIDS Prevention and Care | 4,261,668.99 |
| CHINA Total |  |  |  |  |  | 13,769,910.00 |
| FAR EAST ASIA UNSPECIFIED | 12110 | Health policy and administrative management | AusAid | 05A055 | Pandemics and other EIDs: programming activities | 38,377.60 |
|  | 12181 | Medical education/training | Other Gov Dept | G05448 | NHMRC Medical Postgraduate Scholarship | 21,875.00 |
|  | 12182 | Medical research | Other Gov Dept | G05450 | NHMRC Project Grant | 31,750.00 |
|  | 12250 | Infectious disease control | AusAid | 047S01 | Emerging Zoonotic Diseases | 30,702.27 |
|  |  |  |  | 06A067 | CARE Australia - AIPR Program - Design | 50,000.00 |
|  |  |  |  | 06A129 | Technical Advisory Group (TAG) | 39,916.30 |
|  |  |  |  | 06A435 | ASEAN component - Design Mission - May 2006 | 60,175.47 |
|  |  |  |  | 06A548 | CARE Australia - Mekong AI PLRR Program - Inception | 1,231,706.00 |
|  |  |  |  | 06A599 | Contribution to World Bank Trust Fund, June 2006 | 5,000,000.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04159 | Building evidence based research and practice in South East Asia: Impact on pregnancy and childbirth care and outcomes | 317,040.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 017K0E | Asia Regional HIV/AIDS Project | 2,683,202.26 |
|  |  |  |  | 057M05 | SEA HIV/AIDS Regional Program (SHARP) | 136,596.06 |
| FAR EAST ASIA UNSPECIFIED Total |  |  |  |  |  | 9,641,340.96 |
| FIJI | 12191 | Medical services | Other Gov Dept | G04449 | Donation of dental van to the Fijian National Government | 0.00 |
|  | 12220 | Basic health care | AusAid | 028K09 | Fiji Health Sector Improvement Program | 3,434,357.66 |
|  |  |  |  | 978K1H | Taveuni Health Project | 9,270.63 |
|  |  |  | Other Gov Dept | G03092 | Pathology Services / Virology Services | 0.00 |
|  |  |  |  | G05449 | NHMRC Postgraduate Scholarship | 20,844.00 |
|  | 12281 | Health personnel development | Other Gov Dept | G04225 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04165 | The Pacific OPIC study: A four country s | 80,028.00 |
| FIJI Total |  |  |  |  |  | 3,544,500.29 |
| GLOBAL UNSPECIFIED | 12110 | Health Policy & Administrative Management | Other Gov Dept | G99505 | World Health Organisation (WHO) Core Payment | 6,434,528.16 |
|  |  | Health policy and administrative management | AusAid | 019308 | Int'l Health Program Small Activities | 69,000.00 |
|  |  |  |  | 029C01 | Health Population & Gender Monitoring & Evaluation | 70,230.97 |
|  |  |  |  |  | HPG meetings, seminars & conferences | 148,411.36 |
|  |  |  |  | 05A035 | Aid expertise and research assistance | 113,321.32 |
|  |  |  |  | 06A394 | Additional WHO voluntary Health Sector Strengthening 2005-06 | 1,000,000.00 |
|  | 12181 | Medical education/training | Other Gov Dept | G03076 | WHO Fellowship Program | 66,548.00 |
|  | 12182 | Medical research | Other Gov Dept | G99498 | International Agency for Research on Cancer | 856,331.02 |
|  | 12191 | Medical services | AusAid | 05A098 | AusAID Preparedness for Avian Influenza Response | 51,330.06 |
|  |  |  |  |  | HES Preparedness for AI Response - PPE & Red R | 305,293.81 |
|  |  |  |  | 06A542 | Avian Influenza Simulation Exercise | 204,764.29 |
|  |  |  |  | 06A543 | UNDP AHI (Avian and Human Influenza) Contribution | 500,000.00 |
|  |  |  | Other Gov Dept | G02107 | Spectacles | 16,000.00 |
|  | 12220 | Basic health care | AusAid | 049C03 | Zonta Birthing Kits Project | 200,000.00 |
|  |  |  |  | 06A232 | UNFPA 2005-06 | 2,000,000.00 |
|  |  |  |  | 06A388 | WHO Family and Community Health 2005-06 | 900,000.00 |
|  |  |  |  | 06A390 | WHO Health Tech & Pharm Essential Drugs 2005-06 | 680,000.00 |
|  |  |  |  | 06A393 | Additional WHO Family and Community Health 2005-06 | 500,000.00 |
|  |  |  |  | 06A716 | ICRC Special Mine Action Appeal 2006 | 2,000,000.00 |
|  |  |  |  | 929G24 | International Centre for Diarrhoeal Disease Research | 500,000.00 |
|  |  |  | Other Gov Dept | G05451 | NHMRC Project Grant/Clinical Trial | 172,168.76 |
|  | 12240 | Basic nutrition | AusAid | 06A293 | ICCIDD 20005-06 | 1,050,000.00 |
|  | 12250 | Infectious disease control | AusAid | 047C02 | Thailand HIV/AIDS Project Re-evaluation | 3,187.00 |
|  |  |  |  | 06A387 | WHO HIV/AIDS, TB and Malaria 2005-06 | 2,380,000.00 |
|  |  |  |  | 06A391 | WHO Vaccines and Biologicals 2005-06 | 1,700,000.00 |
|  |  |  |  | 06A392 | WHO Communicable Diseases/Surveillance 2005-06 | 440,000.00 |
|  |  |  |  | 06A395 | WHO Additional voluntary contribution Poliomyelitis | 500,000.00 |
|  |  |  |  | 06A586 | ICRC- HIV/AIDS & Tuberculosis | 75,000.00 |
|  |  |  |  | 06A711 | Global Fund for Vaccines and Immunization | 6,813,845.73 |
|  | 12261 | Health education | AusAid | 06A389 | WHO Chronic Diseases and Health Promotion 2005-06 | 450,000.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04163 | Enterovirus 71 in the Asia Pacific region: reverse genetic approaches to virus surveillance and vaccine development | 132,972.00 |
|  | 13020 | Reproductive health care | AusAid | 06A253 | IPPF voluntary core funding contribution 2005-06 | 1,125,000.00 |
|  | 13030 | Family planning | AusAid | 06A232 | UNFPA 2005-06 | 2,000,000.00 |
|  |  |  |  | 06A253 | IPPF voluntary core funding contribution 2005-06 | 1,125,000.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 029C0A | HIV/AIDS TASKFORCE | 253,146.52 |
|  |  |  |  | 049301 | Global Fund to fight AIDS, TB & Malaria | 15,000,000.00 |
|  |  |  |  | 049C04 | HIV/AIDS Strategy Implementation | 2,299,825.31 |
|  |  |  |  | 049C06 | HIV/AIDS Cluster Evaluation | 145,879.52 |
|  |  |  |  | 059K01 | Staff Training on HIV/AIDS | 11,416.42 |
|  |  |  |  | 06A387 | WHO HIV/AIDS, TB and Malaria 2005-06 | 450,000.00 |
|  |  |  |  | 959G11 | Joint UN Program on HIV/AIDS (UNAIDS) | 4,000,000.00 |
|  |  |  |  | 997S05 | HIV/AIDS & Related International Congresses | 44,226.54 |
| GLOBAL UNSPECIFIED Total |  |  |  |  |  | 56,787,426.78 |
| INDIA | 12182 | Medical research | Other Gov Dept | G05454 | Project Grant | 200,000.00 |
|  | 12220 | Basic health care | AusAid | 056K03 | HIV/AIDS PROGRAM FOR NORTH EAST INDIA | 900,000.00 |
| INDIA Total |  |  |  |  |  | 1,100,000.00 |
| INDONESIA | 12110 | Health Policy & Administrative Management | Other Gov Dept | G02339 | Consultancy on Reviewing Medical Device Regulatory System | 0.00 |
|  |  |  |  | G02340 | Meeting with Expert Advisory Panel on Therapeutic Goods Regulation | 0.00 |
|  |  |  |  | G04231 | "Comparative study tour to TGA by a senior Indonesian delegation on the regulation of medicines, 25-29 October 2004" | 0.00 |
|  |  | Health policy and administrative management | AusAid | 007R09 | Health Services TA- ADB DHS Project | 400,000.00 |
|  |  |  |  | 987G03 | Technical Advisory Facility - Health | 132,063.58 |
|  | 12220 | Basic health care | AusAid | 047604 | Improving Maternal Health in Eastern Indonesia | 95,855.86 |
|  |  |  |  | 06A254 | Nabire HDM Personnel Salary and Benefit | 190,358.90 |
|  |  |  | Other Gov Dept | G04441 | The second comparative study tour to the TGA by a senior Indonesian delegation on the regulation of medicines on 24 and 25 August 2005. | 0.00 |
|  | 12230 | Basic health infrastructure | AusAid | 037K06 | Bali Memorial Package | 2,192,282.84 |
|  |  |  |  | 057K08 | AIPRD Aceh Health Assistance Program | 10,867,745.09 |
|  |  |  |  | 057K10 | AIPRD Aceh Construction - Short Term | 2,316,471.96 |
|  | 12250 | Infectious disease control | AusAid | 05720B | Poliomyelitis Outbreak Response | 1,826,602.60 |
|  |  |  |  | 057602 | World Health Organisation | 1,301,376.81 |
|  |  |  |  | 06A054 | APAC Health Services | 27,167.44 |
|  |  |  |  | 06A090 | Department of Agriculture, Fisheries & Forestry | 16,315.17 |
|  |  |  |  | 06A091 | UN Food & Agriculture Organization (FAO) | 2,278,444.51 |
|  |  |  |  | 06A092 | Communicable Disease Program Support Costs | 13,718.40 |
|  |  |  |  | 06A207 | Epidemiologist Placement - Indonesia | 234,134.00 |
|  |  |  |  | 007R01 | WB WS&S for Low Income Communities Ph II | 2,251,473.45 |
|  | 12261 | Health education | AusAid | 057K13 | Kanaivasu: Aceh Trauma Counselling | 994,254.23 |
|  | 13020 | Reproductive health care | AusAid | 05A051 | Health Sector Programming | 197,929.64 |
|  |  |  |  | 987G03 | Technical Advisory Facility - Health | 427,374.54 |
|  |  |  |  | 987K07 | Women's Health and Family Welfare | 5,810,009.31 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 057K0Q | HIV/AIDS Coordinator | 55,638.29 |
|  |  |  |  |  | HIV/AIDS Development Program | 23,541.40 |
|  |  |  |  | 997K13 | HIV/AIDS Prevention & Care Ph 2 | 9,510,801.30 |
| INDONESIA Total |  |  |  |  |  | 41,163,559.42 |
| KIRIBATI | 12110 | Health policy and administrative management | AusAid | 058K09 | KAP II | 900,861.06 |
|  |  |  |  | 06A144 | Measles-Rubella Vaccination Program | 0.00 |
|  |  |  |  | 06A526 | Tuberculosis epidemic control | 1,173,530.00 |
|  |  |  |  | 06A577 | Household Expenditure and Income Survey | 134,000.00 |
|  | 12181 | Medical education/training | AusAid | 06A344 | Feasibility Design Study | 59,407.51 |
|  | 12191 | Medical services | Other Gov Dept | G04167 | Pathology Services to Kiribati | 0.00 |
|  | 12250 | Infectious disease control | AusAid | 058K09 | Partnerships in Vulnerability Reduction | 27,274.51 |
| KIRIBATI Total |  |  |  |  |  | 2,295,073.08 |
| LAO PEOPLE'S DEMOCRATIC REPUBLIC | 12220 | Basic health care | AusAid | 007K1J | Developing Healthy Communities | 34,864.72 |
|  | 12250 | Infectious disease control | AusAid | 06A208 | Epidemiologist Placement - Lao PDR | 208,936.87 |
| LAO PEOPLE'S DEMOCRATIC REPUBLIC Total |  |  |  |  |  | 243,801.59 |
| MONGOLIA | 12281 | Health personnel development | Other Gov Dept | G04227 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
| MONGOLIA Total |  |  |  |  |  | 0.00 |
| MYANMAR | 12220 | Basic health care | AusAid | 056601 | UNICEF Addressing Vitamin B! Deficiency in Myanmar | 830,000.00 |
|  |  |  |  | 06A694 | Fund for HIV/AIDS in Burma (FHAM) | 1,000,000.00 |
|  | 12240 | Basic nutrition | AusAid | 016K04 | Nutritional Anaemia Initiative | 77,855.63 |
|  | 12250 | Infectious disease control | AusAid | 06A630 | WHO Burma - Avian Influenza Appeal | 280,000.00 |
|  |  |  |  | 06A685 | FAO Burma - Avian Influenza Appeal | 220,000.00 |
|  | 12261 | Health education | AusAid | 036Q05 | CARE: Border Area Chin State Health Improvement | 159,462.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 036Q02 | UNICEF: HIV/AIDS Prevention & Care | 208,175.00 |
|  |  |  |  | 036Q04 | ARC: Kyaingtung Communities Health & HIV | 187,107.00 |
| MYANMAR Total |  |  |  |  |  | 2,962,599.63 |
| NAURU | 12110 | Health Policy & Administrative Management | Other Gov Dept | G04305 | Medical Coordinator | 33,986.59 |
|  |  | Health policy and administrative management | AusAid | 058K0I | Nauru Health Sector Program | 957,164.14 |
|  | 12191 | Medical services | Other Gov Dept | G04308 | High Dependency Unit | 149,850.93 |
|  | 12230 | Basic health infrastructure | Other Gov Dept | G04304 | Hospital Refurbishment | 29,902.50 |
|  |  |  |  | G04307 | Purchase of Pharmaceuticals | 283,465.21 |
| NAURU Total |  |  |  |  |  | 1,454,369.37 |
| NEPAL | 12220 | Basic health care | AusAid | 996M01 | National Vitamin A Expansion Program | 600,210.48 |
|  | 12250 | Infectious disease control | AusAid | 06A094 | Support to WHO Nepal polio immunisation | 145,013.19 |
| NEPAL Total |  |  |  |  |  | 745,223.67 |
| OCEANIA UNSPECIFIED | 12110 | Health policy and administrative management | AusAid | 018S02 | Minor Activities Health Projects | 102,595.43 |
|  |  |  |  | 028S01 | Fiji School of Medicine | 500,000.00 |
|  |  |  |  | 048G01 | Fiji Women's Crisis Centre Phase 4 | 39,289.75 |
|  |  |  |  | 058S02 | UNICEF Pacific Program | 1,900,000.00 |
|  |  |  |  | 888I14 | SPC Core Budget | 10,013,480.00 |
|  |  |  |  | 888J40 | Secretariat South Pacific Regional Environment Programme (SPREP) | 1,400,000.00 |
|  |  |  |  | 988K0A | Pacific Action for Health NCD project | 41,000.00 |
|  |  |  |  | 998K0Q | Pacific Regional HIV/AIDS Project | 1,263,217.76 |
|  |  |  |  | 998S01 | POPs Project Phase II | 1,432,549.61 |
|  | 12181 | Medical education/training | AusAid | 028S01 | Fiji School of Medicine | 250,000.00 |
|  |  |  |  | 988G01 | Medical Equipment Maintenance Project | 38,357.72 |
|  | 12191 | Medical services | AusAid | 018K0J | Tertiary Health Phase III | 1,355,370.79 |
|  | 12261 | Health education | AusAid | 018S02 | Minor Activities Health Projects | 14,684.66 |
|  | 13020 | Reproductive health care | AusAid | 998K09 | SP Reproductive Health and FP Training | 402,112.46 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 018K0Q | UNAIDS HIV/AIDS project in the Pacific | -80,360.00 |
|  |  |  |  | 998K0Q | Pacific Regional HIV/AIDS Project | 1,974,383.11 |
|  |  |  | Other Gov Dept | G05453 | Postgraduate Scholarships | 17,515.12 |
| OCEANIA UNSPECIFIED Total |  |  |  |  |  | 20,664,196.41 |
| PAKISTAN | 12230 | Basic health infrastructure | AusAid | 016K03 | Pakistan-Australia District Eye Care | 397,940.00 |
| PAKISTAN Total |  |  |  |  |  | 397,940.00 |
| PAPUA NEW GUINEA | 12110 | Health policy and administrative management | AusAid | 008K01 | Sector Monitoring and Review | 993,298.39 |
|  |  |  |  | 018M0A | PNG IMR Support Program | 974,472.90 |
|  |  |  |  | 038K02 | Health Sector Resourcing Framework | 3,065,556.18 |
|  |  |  |  | 048K0I | Health: Capacity Building Service Centre | 8,535,782.12 |
|  |  |  |  | 05A083 | Financial Management Support to MSB – Deloitte | 164,189.78 |
|  |  |  |  | 958K02 | Health: Program Development Fund | 305,384.36 |
|  |  |  |  | 968K0Y | Health Pharmaceutical Upgrade Project | 1,789,828.81 |
|  |  |  |  | 988K1N | Health Services Support Program | 7,877,429.54 |
|  | 12181 | Medical education/training | AusAid | 028K0K | UPNG Medical School Support Program | 5,566.41 |
|  |  |  |  |  | UPNG Medical School Support Program - Grant | 425,607.00 |
|  | 12182 | Medical research | AusAid | 018M0A | PNG IMR Support Program | 1,112,806.10 |
|  |  |  | Other Gov Dept | G05450 | NHMRC Project Grant | 176,500.00 |
|  | 12191 | Medical services | AusAid | 028K0I | Tertiary Health Services Phase 3 | 552,104.60 |
|  | 12220 | Basic health care | AusAid | 948H00 | Health-Women & Child Health Project | 101,884.57 |
|  |  |  |  | 988K1N | Health Services Support Program | 8,119,528.99 |
|  |  |  | Other Gov Dept | G03291 | Pathology Services to PNG | 0.00 |
|  | 12230 | Basic health infrastructure | AusAid | 058G03 | Torres Strait Treaty Zone Health Partner | 131,263.83 |
|  |  |  |  | 988K1K | Bouganville: Health & Reconstruction Personnel | -6,603.00 |
|  | 12250 | Infectious disease control | AusAid | 048K0G | Design | 260,085.03 |
|  |  |  |  | 05A063 | Strategic Director | 20,150.32 |
|  |  |  |  | 06A267 | Transition Period | 278,860.64 |
|  |  |  |  | 06A396 | ISMPP selection & design | 8,886.14 |
|  |  |  |  | 06A674 | Condom Social Marketing | 2,783,631.00 |
|  |  |  |  | 988K19 | Central Public Health Laboratory Project | 351,057.00 |
|  |  |  | Other Gov Dept | G03093 | PNG and Queensland Health Collaborative Meeting | 0.00 |
|  | 12281 | Health personnel development | AusAid | 06A797 | WHO Tech Support to Health Sector in PNG | 768,601.80 |
|  |  |  | Other Gov Dept | G04230 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04156 | Research and training to reduce morbidity and mortality from malaria in Papua (Indonesia) and Papua New Guinea | 329,966.00 |
|  |  |  |  | G04160 | Neonatal immunisation with pneumococcal conjugate vaccine in Papua New Guinea | 236,394.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 048K0G | Design | 43,298.55 |
|  |  |  |  |  | PNG-Australia HIV/AIDS Support Program | 186,017.64 |
|  |  |  |  | 05A063 | Strategic Director | 16,938.40 |
|  |  |  |  | 978K21 | National HIV/AIDS Support Project | 13,324,482.69 |
| PAPUA NEW GUINEA Total |  |  |  |  |  | 52,932,969.79 |
| PHILIPPINES | 12181 | Medical education/training | AusAid | 06A673 | Avian & Pandemic Influenza Preparedness | 200,000.00 |
|  | 12220 | Basic health care | AusAid | 99760A | Australian Contribution to UNICEF CPC5 | 73.62 |
|  |  |  |  | 997K16 | Health Strategy | -6.87 |
|  | 12250 | Infectious disease control | AusAid | 957G60 | Malaria Control and Prevention Project | 86,272.53 |
|  | 12261 | Health education | AusAid | 047605 | WHO Mindanao Malaria Project | 908,866.21 |
|  | 13010 | Population policy and administrative management | AusAid | 06A141 | Contribution to the Maternal Mortality Survey 2006 | 19,262.41 |
|  | 13081 | Personnel development for population and reproductive health | AusAid | 047G08 | Support for Population Initiatives | 630,137.96 |
|  |  |  |  | 06A423 | Sponsorship - International Conference on RH Mgmt | 6,617.50 |
| PHILIPPINES Total |  |  |  |  |  | 1,851,223.36 |
| SAMOA | 12110 | Health policy and administrative management | AusAid | 05A102 | Samoa Health ISP Extension Phase | 528,844.92 |
|  |  |  |  | 988K02 | Samoa Health ISP | 692,753.98 |
| SAMOA Total |  |  |  |  |  | 1,221,598.90 |
| SOLOMON ISLANDS | 12110 | Health policy and administrative management | AusAid | 008K0D | Health Institutional Strengthening Project | 4,775,985.63 |
|  |  |  |  | 05A049 | Health Sector Trust Account | 7,800,000.00 |
|  |  |  |  | 05A050 | Health Sector SWAP Design | 7,044.26 |
|  |  |  |  | 998K0Q | Pacific Regional HIV/AIDS Project | 30,114.91 |
|  | 12220 | Basic health care | AusAid | 038Q07 | NGO CA: ADRA Community Strengthening & Reconciliation | 300,000.00 |
|  |  |  | Other Gov Dept | G03092 | Pathology Services / Virology Services | 0.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 998K0Q | Pacific Regional HIV/AIDS Project | 47,068.97 |
| SOLOMON ISLANDS Total |  |  |  |  |  | 12,960,213.77 |
| SOUTH & CENTRAL ASIA UNSPECIFIED | 12220 | Basic health care | AusAid | 056301 | Partnership Agreement in South Asia | 1,500,000.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 016K05 | South Asia Health Initiative | 1,631,077.29 |
| SOUTH & CENTRAL ASIA UNSPECIFIED Total |  |  |  |  |  | 3,131,077.29 |
| SOUTH OF SAHARA UNSPECIFIED | 12220 | Basic health care | AusAid | 992M0D | Australian Partnerships with African Communities | 67,264.69 |
|  | 12230 | Basic health infrastructure | AusAid | 012K01 | Fistula Hospital - Rural Village Project | 1,000,000.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 032M01 | Enhancing community support systems. | 1,772,709.00 |
|  |  |  |  | 032M02 | Enhancing Effective Responses to HIVAIDS | 1,314,777.00 |
|  |  |  |  | 032M03 | Reducing Community Vulnerability to HIV | 2,071,932.00 |
| SOUTH OF SAHARA UNSPECIFIED Total |  |  |  |  |  | 6,226,682.69 |
| SRI LANKA | 12220 | Basic health care | AusAid | 996601 | Early Childhood Care and Development- NIP Ph 2 | -788,424.00 |
|  | 12240 | Basic nutrition | AusAid | 996601 | Early Childhood Care and Development- NIP Ph 2 | 1,576,848.00 |
|  | 12281 | Health personnel development | Other Gov Dept | G04229 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04157 | Reducing deaths from pesticides poisoning: Establishing a regional toxicology research centre | 73,873.00 |
| SRI LANKA Total |  |  |  |  |  | 862,297.00 |
| THAILAND | 12220 | Basic health care | Other Gov Dept | G04045 | Pathology Services/Virology Services | 0.00 |
|  |  |  |  | G04437 | A comprehensive visiting program for the senior delegation from the Thai Food and Drug Administration (FDA) | 0.00 |
|  |  |  |  | G04438 | A practical training program on vaccine quality assurance for a senior official from the Thai Food and Drug Administration (FDA) | 0.00 |
|  |  |  |  | G04440 | A training program on the regulation of prescription medicines for a senior official from the Thai Food and Drug Administration (FDA) | 0.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04161 | Burden of disease and cost effectiveness of intervention options: Informing policy choices and health system reform in Thailand. | 157,596.00 |
|  |  |  |  | G04164 | Thai health risk transition: A national cohort stud | 246,244.00 |
| THAILAND Total |  |  |  |  |  | 403,840.00 |
| TIMOR-LESTE | 12110 | Health policy and administrative management | AusAid | 017K04 | Specialist Services Project | 453,276.68 |
|  |  |  |  | 06A078 | Health Sector Design Framework Mission | 62,884.13 |
|  |  |  |  | 06A221 | Health Sector Design Framework | 54,330.00 |
|  |  |  |  | 06A235 | East Timor HIV/AIDS Program | 5,389.32 |
|  | 12181 | Medical education/training | Other Gov Dept | G04450 | East Timor Eye Program | 0.00 |
|  | 12191 | Medical services | AusAid | 017K04 | Specialist Services Project | 346,832.06 |
|  |  |  |  | 06A223 | Specialist Medical Services Support Project Design | 24,084.50 |
|  |  |  |  | 06A306 | Strengthening Immunization Plus | 800,000.00 |
|  |  |  |  | 06A475 | Appraisal of the Draft Design | 17,381.85 |
|  | 12220 | Basic health care | AusAid | 057M03 | Health Sector Support Program | 56,033.96 |
|  |  |  | Other Gov Dept | G04069 | Dili Hospital Laundry Project | 114,097.00 |
|  | 12281 | Health personnel development | AusAid | 017K0W | National Mental Health Project | 37,921.20 |
| TIMOR-LESTE Total |  |  |  |  |  | 1,972,230.70 |
| TONGA | 12110 | Health policy and administrative management | AusAid | 038K0H | Health Management Project Phase III | 230,509.70 |
|  |  |  |  |  | Implementation | 138,862.08 |
|  |  |  |  | 978K0I | Health Sector Management Project | 63,718.00 |
|  | 12191 | Medical services | AusAid | 06A588 | Tonga Earthquake Assistance | 150,000.00 |
|  | 13010 | Population Policy & Administrative Management | Other Gov Dept | G04165 | The Pacific OPIC study: A four country s | 80,028.00 |
| TONGA Total |  |  |  |  |  | 663,117.78 |
| UGANDA | 12181 | Medical education/training | Other Gov Dept | G05630 | Ugandan Nurse Education - Observational Visit | 4,199.20 |
| UGANDA Total |  |  |  |  |  | 4,199.20 |
| VANUATU | 12110 | Health policy and administrative management | AusAid | 968K1Y | Health Sector Assistance | 1,157,447.85 |
|  |  |  |  | 998K0Q | Pacific Regional HIV/AIDS Project | 35,127.66 |
|  | 12281 | Health personnel development | AusAid | 988K1L | Village Health Worker Project | 361,571.00 |
|  | 13040 | STD control including HIV/AIDS | AusAid | 998K0Q | Pacific Regional HIV/AIDS Project | 54,903.80 |
| VANUATU Total |  |  |  |  |  | 1,609,050.31 |
| VIET NAM | 12220 | Basic health care | Other Gov Dept | G04439 | A visiting program on medicine regulation for a senior Vietnamese delegation on 8 June 2005 | 0.00 |
|  | 12250 | Infectious disease control | AusAid | 057R06 | Public Health Emergency Management | 1,200,000.00 |
|  |  |  |  | 06A206 | Epidemiologist Placement - Vietnam | 230,647.00 |
|  | 12281 | Health personnel development | Other Gov Dept | G04226 | "UMC @ TGA Pharmacovigilance Training Course, 8-19 November 2004" | 0.00 |
| VIET NAM Total |  |  |  |  |  | 1,430,647.00 |
| Grand Total |  |  |  |  |  | 241,785,251.37 |
| Education 2005/06 expenses (provisional) |  |  |  |  |  |  |
| AFGHANISTAN | 11220 | Primary education | AusAid | 046105 | CARE Education Project | 1,105,904.10 |
|  | 43081 | Multisector education/training | AusAid | 046101 | Afghanistan Scholarships | 19,314.08 |
| BANGLADESH | 11220 | Primary education | AusAid | 986R04 | UNICEF Primary Education | 2,512,837.00 |
|  | 43081 | Multisector education/training | AusAid | 896F07 | Bangladesh - ADS | 2,588,052.66 |
| BHUTAN | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 896F00 | Bhutan - ADS | 1,048,239.54 |
| BRAZIL | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05486 | Delegations from Brazil and Colombia | 33,063.00 |
| CAMBODIA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G04046 | Technical Cooperation | 0.00 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 937F00 | Cambodia - ADS | 1,704,837.94 |
| CHILE | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05485 | Chile English Language Delegation to Australia | 0.00 |
|  | 11330 | Vocational training | Other Gov Dept | G05458 | Chilean VET Advisory Council Delegation to Australia | 0.00 |
| CHINA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G04188 | Australia China Higher Education (Shandong) Forum July 2004 | 0.00 |
|  |  |  |  | G04189 | Chinese University Administrators Shadowing (ChUAS 2004) Project | 0.00 |
|  | 11330 | Vocational training | AusAid | 997K07 | Chongqing Vocational Education &Training | 3,571,790.92 |
|  |  |  | Other Gov Dept | G05602 | Australia China Senior VET Mentoring 2005 | 144,648.00 |
|  | 11420 | Higher education | Other Gov Dept | G02263 | Higher Education Strategic Exchange Initiative | 0.00 |
|  |  |  |  | G02312 | Australia - Asia Awards - China | 42,128.39 |
|  |  |  |  | G05601 | Chinese University Administrators Shadowing (CHUAAS 2005) | 45,000.00 |
|  |  |  |  | G05698 | Training Exchange with Chinese MFA | 5,125.00 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 877F00 | China - ADS | 1,810,638.80 |
| COLOMBIA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05486 | Delegations from Brazil and Colombia | 0.00 |
| COOK ISLANDS | 43081 | Multisector education/training | AusAid | 888C00 | Cook Islands - ARDS | 115,713.11 |
| CROATIA | 43081 | Multisector education/training | Other Gov Dept | G02258 | Australia-Europe Scholarships | 0.00 |
| FAR EAST ASIA UNSPECIFIED | 11130 | Teacher training | Other Gov Dept | G02327 | SEAMEO - Australia Project on Teaching Through ICTs | 0.00 |
|  | 11330 | Vocational training | AusAid | 047K0F | Child Wise | 264,226.00 |
|  | 11430 | Advanced technical and managerial training | AusAid | 977S03 | Singapore Third Country Training Program | 18,262.37 |
| FIJI | 11110 | Education policy and administrative management | AusAid | 028K0H | Education Sector Support Program | 5,491,123.66 |
|  | 11182 | Educational research | AusAid | 06A285 | Independent review | 15,863.84 |
|  | 11220 | Primary education | AusAid | 998K0A | Lautoka Teacher's College Project | 334.99 |
|  | 11430 | Advanced technical and managerial training | AusAid | 888C03 | In-country Short Course Training | 356,574.32 |
|  |  |  | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 0.00 |
|  | 43081 | Multisector education/training | AusAid | 888F01 | Fiji - ADS | 556,384.79 |
|  |  |  |  | 998L02 | Fiji - ARDS | 1,828,569.35 |
| GLOBAL UNSPECIFIED | 11420 | Higher education | AusAid | 06A459 | Australian Leadership Awards | 473,796.80 |
|  | 43081 | Multisector education/training | AusAid | 000C05 | ADS Information Kit Preparation Project | 6,648.50 |
|  |  |  |  | 029C0C | Australian Development Gateway | 381,762.34 |
|  |  |  |  | 039212 | Humanitarian and Emergency Training | 18,972.80 |
|  |  |  |  | 959C09 | Student Program Section Cross Regional | 207,530.13 |
|  |  |  | Other Gov Dept | G03094 | Schooling for dependants of AusAID scholarship holders | 0.00 |
|  |  |  |  | G05469 | IDP Peace Scholarships | 20,000.00 |
| GRENADA | 11230 | Basic life skills for youth and adults | AusAid | 06A692 | Post hurricane Ivan rehabilitation - Grenada | 535,000.00 |
| INDIA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05693 | Global Communities for Sustainability | 35,000.00 |
|  | 11220 | Primary education | AusAid | 966R01 | UNICEF Primary Education | 1,451,897.00 |
|  | 11420 | Higher education | Other Gov Dept | G02265 | Higher Education Strategic Initiative | 0.00 |
|  |  |  |  | G02314 | Australia - Asia Awards - India | 0.00 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
| INDONESIA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G02008 | GSLP on Curriculum and Assessment Reform in Indonesia | 0.00 |
|  |  |  |  | G03285 | International Regional Heads of Education Forum | 0.00 |
|  |  | Education policy and administrative management | AusAid | 037K0D | Indonesia Education TAG | 180,538.10 |
|  |  |  |  | 057K0H | BEP preparation, advisory & mgmt (AIPRD grants) | 1,586,128.30 |
|  | 11120 | Education Facilities & Training | Other Gov Dept | G04252 | Central Java (Indonesia) Queensland Guest Teacher and Student Exchange Program | 0.00 |
|  |  | Education facilities and training | AusAid | 047K0A | Kang Guru Radio English (KGRE) | 505,954.90 |
|  |  |  |  | 057K0A | AIPRD Aceh Education Assistance Project | 7,303,748.21 |
|  |  |  |  | 057K0H | AIPRD Basic Education Programming | 165,226.83 |
|  |  |  |  | 057K11 | Aceh Construction Program | 6,514,655.59 |
|  |  |  |  | 05A032 | Scoping Mission | 37,294.89 |
|  | 11130 | Teacher training | AusAid | 047K01 | LAPIS | 2,596,018.56 |
|  |  |  |  | 047K09 | Islamic Schools English Language Project | 721,634.17 |
|  |  |  | Other Gov Dept | G02267 | Language Teacher Exchange Program | 0.00 |
|  |  |  |  | G03207 | Central Java ( Indonesia) Queensland Guest Teacher and Student Exchange Program | 0.00 |
|  |  |  |  | G03275 | SEAMEO Australia ICT Implementation Plan Project | 0.00 |
|  | 11182 | Educational research | AusAid | 027R06 | Education Sector Program Development | 315,561.25 |
|  |  |  |  | 057K0W | AIPRD Educational Research and Training | 31,437.49 |
|  | 11220 | Primary education | AusAid | 037601 | Creating Learning Communities for Children | 689,449.52 |
|  |  |  |  | 037K0A | Partnership in Basic Education | 2,357,184.11 |
|  |  |  |  | 047209 | CAP 2004: Education: SCF(UK) | 415,747.00 |
|  |  |  |  | 057K0H | AIPRD Basic Education Programming | 605,670.80 |
|  |  |  |  | 05A032 | Scoping Mission | -2,465.00 |
|  |  |  | Other Gov Dept | G04435 | Book Program | 0.00 |
|  | 11240 | Early childhood education | AusAid | 007K29 | NTT Primary Education Partnership | 4,643,931.28 |
|  | 11320 | Secondary education | Other Gov Dept | G02266 | distance Education Project (SEAMOLEC) | 0.00 |
|  | 11330 | Vocational training | AusAid | 047M01 | VET program development | 199,032.61 |
|  |  |  |  | 057K0I | AIPRD Skills and Training Programming | 5,531.59 |
|  | 11420 | Higher education | AusAid | 057K0F | AIPRD Scholarships Program | 8,300,227.06 |
|  |  |  |  | 057K0W | AIPRD Educational Research and Training | 10,640.18 |
|  |  |  | Other Gov Dept | G02268 | University Research Management Project | 0.00 |
|  |  |  |  | G02315 | Australia - Asia Awards - Indonesia | 27,783.75 |
|  |  |  |  | G02329 | Indonesia Higher Education Strategic Exchange Initiative Project | 0.00 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 037K04 | ADS Off-Shore Management - Phase II | 3,619,491.03 |
|  |  |  |  | 037K05 | Specialised Training Project - Phase III | 17,542,867.19 |
|  |  |  |  | 897F01 | English Language Training Activities | 31,971.10 |
|  |  |  |  | 957L02 | INDONESIA - ADS | 33,952,276.06 |
|  |  |  | Other Gov Dept | G02009 | Merdeka Fellowships | 0.00 |
|  |  |  |  | G04134 | South Australia Scholarship for Indonesian Inagrasi Students | 0.00 |
| KIRIBATI | 11110 | Education policy and administrative management | AusAid | 058K0A | Education Sector Support | 6,734.87 |
|  |  |  |  | 988K08 | Education Sector Program | 1,099,051.02 |
|  | 11430 | Advanced technical and managerial training | AusAid | 06A145 | Nurse Upskilling Study | 32,000.00 |
|  |  |  |  | 968L04 | Training - In-Country | 151,708.00 |
|  | 43081 | Multisector education/training | AusAid | 888C05 | Kiribati - ARDS | 1,247,256.64 |
|  |  |  |  | 888F03 | Kiribati - ADS | 363,571.52 |
| LAO PEOPLE'S DEMOCRATIC REPUBLIC | 11220 | Primary education | AusAid | 047R05 | ABEL Design Costs | 36,353.23 |
|  |  |  |  |  | Access to Basic Education | 6,587.63 |
|  |  |  |  |  | Design, Implementation & Management Costs | 2,505,232.53 |
|  |  |  |  | 987R08 | ADB - LAOS BASIC EDUCATION GIRLS PROJECT | 503,855.59 |
|  | 11430 | Advanced technical and managerial training | AusAid | 057K0L | Interpreter Training for MFA | 30,308.64 |
|  | 43081 | Multisector education/training | AusAid | 897F05 | Laos - ADS | 4,186,132.01 |
|  |  |  |  | 957C02 | Pre-departure English Course | 607,597.62 |
| MALAYSIA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G02270 | Quality Assurance Study Visit | 0.00 |
|  |  |  |  | G03288 | International Regional Heads of Education Forum | 0.00 |
|  | 11220 | Primary education | Other Gov Dept | G02328 | Australia - Malaysia Science Education Collaboration Visit to WA | 0.00 |
|  | 11420 | Higher education | Other Gov Dept | G02079 | Australia-Asia Fellowships | 0.00 |
|  |  |  |  | G02271 | University Lecturer Upgrade Program | 0.00 |
|  |  |  |  | G02317 | Australia - Asia Awards - Malaysia | 40,548.64 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
| MALDIVES | 43081 | Multisector education/training | AusAid | 896F04 | Maldives - ADS | 1,529,373.71 |
| MARSHALL ISLANDS | 43081 | Multisector education/training | AusAid | 898F03 | Marshall Islands - ADS | 22,318.16 |
|  |  |  |  | 918C02 | Marshall Islands - ARDS | 179,874.13 |
| MEXICO | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05487 | Mexican Ministry of Education Delegation to Australia | 0.00 |
| MICRONESIA, FEDERATED STATES OF | 43081 | Multisector education/training | AusAid | 898C07 | FSM - ARDS | 658,816.79 |
|  |  |  |  | 898F02 | FSM - ADS | 275,140.25 |
| MONGOLIA | 43081 | Multisector education/training | AusAid | 937F06 | Mongolia - ADS | 1,024,571.07 |
| MOZAMBIQUE | 11110 | Education Policy & Administrative Management | Other Gov Dept | G02105 | Non Financial Assistance Consultancy | 0.00 |
|  | 43081 | Multisector education/training | AusAid | 002L01 | Moz In-country Scholarship Award Scheme | 145,117.62 |
| MYANMAR | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 0.00 |
| NAURU | 11110 | Education policy and administrative management | AusAid | 058K0H | Nauru Education and Training | 518,835.20 |
|  | 43081 | Multisector education/training | AusAid | 978L04 | Nauru - ARDS | 245,642.10 |
| NEPAL | 43081 | Multisector education/training | AusAid | 896F05 | Nepal - ADS | 1,001,638.67 |
| NIUE | 43081 | Multisector education/training | AusAid | 888C14 | Niue - ARDS | 216,864.31 |
| OCEANIA UNSPECIFIED | 11110 | Education policy and administrative management | AusAid | 05A027 | Small Grants Program | 456,721.35 |
|  |  |  |  | 05A067 | Fiji School of Medicine | 200,000.00 |
|  |  |  |  | 06A313 | Review of PRHFPTP & Pre-feasibility for wider SRH program | 125,755.60 |
|  | 11320 | Secondary education | AusAid | 898J46 | SPBEA SP Board for Education Assessment | 350,000.00 |
|  | 11330 | Vocational training | AusAid | 04 K01 | Security in the Pacific Maritime Sector | 1,029,300.00 |
|  | 11420 | Higher education | AusAid | 928J27 | USP Council / Grants Committee | 28,549.21 |
|  |  |  |  | 948C07 | University of the South Pacific - MoU | 3,300,000.00 |
|  | 11430 | Advanced technical and managerial training | AusAid | 008S02 | Pacific Regional Training Other (short) | -10,485.59 |
|  |  |  |  | 03 K01 | Scholarships for Governance Program | 232,492.18 |
|  |  |  |  | 05A025 | Phase I Study | 365,492.18 |
|  | 43081 | Multisector education/training | AusAid | 06A523 | Support for ODI Fellows 2005 - 2007 | 697.92 |
|  |  |  |  | 918C06 | ARDS (3ct) Administration Fiji | 12,628.58 |
| PAKISTAN | 43081 | Multisector education/training | AusAid | 896F06 | Pakistan - ADS | 1,291,297.15 |
| PALAU | 43081 | Multisector education/training | AusAid | 898C04 | Palau - ARDS | 104,926.50 |
|  |  |  |  | 898F01 | Palau - ADS | 101,577.40 |
| PAPUA NEW GUINEA | 11110 | Education policy and administrative management | AusAid | 018K0W | PNG Education Personnel Payroll Project | 251,479.23 |
|  |  |  |  | 948D02 | Education Sector Development | 346,334.71 |
|  |  |  |  | 988K1E | Education Capacity Building Program | 14,020,529.74 |
|  | 11120 | Education facilities and training | AusAid | 018K0K | PNG-Australia Targeted Training Facility | 5,467,112.09 |
|  |  |  |  | 038K0J | Manus Schools Upgrading Project | 2,226,022.35 |
|  | 11220 | Primary education | AusAid | 018K0L | Basic Education Development Project (BEDP) | 4,823,124.69 |
|  |  |  |  | 968K1L | Primary & Secondary Teacher Education Project (PASTEP) | 57,686.42 |
|  |  |  |  | 978K1T | Curriculum Reform Implementation (CRIP) | 7,734,643.29 |
|  |  |  |  | 988B02 | Education CASP | 411,810.65 |
|  | 11230 | Basic life skills for youth and adults | AusAid | 058K0L | Sport & Development in PNG | 345,769.86 |
|  | 11330 | Vocational training | AusAid | 028K0F | POSSP (Occupational Skills & Standards) | 1,834,317.92 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 958L03 | PNG Australian Development Scholarships (ADS | 13,331,242.56 |
| PHILIPPINES | 11110 | Education policy and administrative management | AusAid | 047K03 | Support for Muslim Education | -26.03 |
|  | 11220 | Primary education | AusAid | 047K04 | Strengthening Implementation of Visayas Education | 1,713,916.40 |
|  |  |  |  | 057G02 | Education Sectoral Advisory Group | 135,670.87 |
|  |  |  |  | 997K0P | Basic Education Assistance for Mindanao | 5,056,590.94 |
|  | 11240 | Early childhood education | AusAid | 047R04 | Australian Contribution to UNICEF CPC6 | 9,464,842.98 |
|  | 11330 | Vocational training | AusAid | 027K05 | PAQTVET Project Phase II | 2,245,091.74 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 887F04 | Philippines - ADS | 3,555,594.18 |
| SAMOA | 11110 | Education policy and administrative management | AusAid | 008K15 | Education Sector PMG | -1,806.75 |
|  |  |  |  | 038K0S | ESPII Detailed Design | 228,822.68 |
|  |  |  |  | 06A276 | PSIF Implementation (Special Purpose Account) | 1,000,000.00 |
|  |  |  |  | 06A277 | PSIF Implementation (CST) | 337,866.70 |
|  |  |  |  | 06A600 | ESPII Implementation | 688,160.39 |
|  |  |  |  | 988K0G | Ministry of Education ISP | 73,196.46 |
|  | 11220 | Primary education | AusAid | 038K0S | Education Sector Approach | 133,517.35 |
|  |  |  |  |  | ESPII Detailed Design | 1,277.11 |
|  |  |  |  | 868G07 | Samoa Small Grants Scheme | 241,583.83 |
|  | 43081 | Multisector education/training | AusAid | 018L01 | Samoa Distance Education Program | 94,063.91 |
|  |  |  |  | 898C20 | Samoa - ARDS | 1,218,007.94 |
|  |  |  |  | 898F09 | Samoa - ADS | 1,281,888.34 |
| SOLOMON ISLANDS | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 898C15 | Solomon Islands - ARDS | 1,035,461.70 |
|  |  |  |  | 898F07 | Solomon Islands - ADS | 1,082,914.57 |
| SOUTH AFRICA | 43081 | Multisector education/training | AusAid | 892F11 | South Africa - ADS | 805.26 |
| SOUTH OF SAHARA UNSPECIFIED | 11110 | Education policy and administrative management | AusAid | 032L02 | Africa-Australia Development Scholarships | 6,991,685.63 |
|  | 11420 | Higher education | AusAid | 012K03 | African Virtual University | 1,374,999.99 |
| SRI LANKA | 11110 | Education Policy & Administrative Management | Other Gov Dept | G03286 | International Regional Heads of Education Forum | 0.00 |
|  | 43081 | Multisector education/training | AusAid | 896F02 | Sri Lanka - ADS | 717,868.79 |
| THAILAND | 11110 | Education Policy & Administrative Management | Other Gov Dept | G03274 | Provision of Speaker at Far Eastern College International Conference | 0.00 |
|  |  |  |  | G03276 | Science Communication Workshop | 0.00 |
|  |  |  |  | G03287 | International Regional Heads of Education Forum | 0.00 |
|  |  |  |  | G99051 | Thailand University Administrators | 0.00 |
|  |  |  |  | G99590 | Thailand school principals mgmt training | 0.00 |
|  | 11220 | Primary education | Other Gov Dept | G02273 | translation of Australian Studies Kit | 0.00 |
|  | 11330 | Vocational training | Other Gov Dept | G03277 | VET Capacity Building: Establishment of Multi-Campus Institute Project | 22,272.73 |
|  |  |  |  | G99048 | Phase 2 National Framework for Technology | 0.00 |
|  | 11420 | Higher education | Other Gov Dept | G02080 | Australia-Asia Fellowships | 0.00 |
|  |  |  |  | G02319 | Australia - Asia Awards - Thailand | 50,508.01 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 897F07 | ADS Thailand | 33,771.93 |
| TIMOR-LESTE | 11110 | Education Policy & Administrative Management | Other Gov Dept | G05466 | East Timor Friendship Schools Project | 30,950.00 |
|  | 11120 | Education Facilities & Training | Other Gov Dept | G05717 | Dili Institute of Technology Staff Exchange Project | 78,415.00 |
|  | 11320 | Secondary education | Other Gov Dept | G03280 | East Timor Scholarships Nudgee International College | 0.00 |
|  | 11420 | Higher education | AusAid | 057L01 | EDUKA scholarships | 241,857.42 |
|  |  |  | Other Gov Dept | G05470 | Infoxchange Technology Audit | 3,740.00 |
|  |  |  |  | G05472 | Xanana Vocational Education Trust Scholarships | 15,000.00 |
|  |  |  |  | G05500 | Employment of a Vocational Education and Institutional Development Advisor for Dili Institute of Technology | 42,500.00 |
|  | 43081 | Multisector education/training | AusAid | 007L02 | East Timor ADS | 1,787,479.58 |
|  |  |  | Other Gov Dept | G02007 | EDUKA scholarships | 20,414.00 |
| TOKELAU | 43081 | Multisector education/training | AusAid | 898C16 | Tokelau - ARDS | 151,462.13 |
| TONGA | 11420 | Higher education | AusAid | 008K14 | Tonga Distance Education | 23,869.37 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 898C17 | Tonga - ARDS | 789,896.76 |
|  |  |  |  | 898F08 | Tonga - ADS | 278,954.09 |
|  |  |  |  | 928C01 | Tonga In-country Training | 195,977.09 |
| TUVALU | 43081 | Multisector education/training | AusAid | 888C24 | Tuvalu - ARDS | 582,529.12 |
|  |  |  |  | 888F06 | Tuvalu - ADS | 175,852.74 |
| VANUATU | 11110 | Education policy and administrative management | AusAid | 06A287 | Transmitter, FMIS, SSEP Books Procurement | 270,396.68 |
|  | 11320 | Secondary education | AusAid | 008K18 | Secondary Schools Extension - Phase 2 | 4,403,865.73 |
|  | 11330 | Vocational training | AusAid | 048K0P | Tech/Vocational Education and Training | 1,408,510.29 |
|  |  |  |  | 928D04 | VIT Institutional Strengthening Project | 22,865.49 |
|  | 11420 | Higher education | AusAid | 048L01 | In-Country Scholarships | 104,865.46 |
|  | 43081 | Multisector education/training | AusAid | 888C09 | ARDS Vanuatu: USP | 1,020,038.37 |
|  |  |  |  | 888C10 | ARDS Vanuatu: Fiji | 227,164.29 |
|  |  |  |  | 888C11 | ARDS Vanuatu: PNG | 955.17 |
|  |  |  |  | 888F04 | Vanuatu - ADS | 786,211.88 |
|  |  |  |  | 948C00 | ARDS Vanuatu: New Caledonia | 83,505.23 |
| VIET NAM | 11182 | Educational research | Other Gov Dept | G05502 | Study in Melbourne Scholarships | 150,000.00 |
|  | 11220 | Primary education | AusAid | 007K21 | English Language Teaching | -650,000.00 |
|  | 11420 | Higher education | Other Gov Dept | G02320 | Australia - Asia Awards - Vietnam | 56,363.50 |
|  | 11430 | Advanced technical and managerial training | Other Gov Dept | G05722 | Customs International Executive Management Program (CIEMP) | 14,110.00 |
|  | 43081 | Multisector education/training | AusAid | 027K0E | Viet Nam ADS - PREP | 2,253,671.66 |
|  |  |  |  | 927D02 | Vietnam - ADS | 16,494,777.34 |
| Grand Total |  |  |  |  |  | 170,696,599.03 |

|  |  |  | Question 25: Attachment C |  |  |
| --- | --- | --- | --- | --- | --- |
| Australia's Official Development Assistance (ODA) |  |  |  |  |  |
| Water and Sanitation, Health and Education Sectors 2005–06 |  |  |  |  |  |
| Country/Region |  | Water and Sanitation ($A)* |  | Health ($A)* | Education ($A)* |
| Afghanistan |  | $0 |  | $745,707 | $1,125,218 |
| Bangladesh |  | $278,567 |  | $0 | $5,100,890 |
| Bhutan |  | $0 |  | $0 | $1,062,350 |
| Botswana |  | $0 |  | $61,905 | $0 |
| Brazil |  | $0 |  | $0 | $33,063 |
| Cambodia |  | $261,996 |  | $938,551 | $1,718,948 |
| China |  | $3,141,330 |  | $13,769,910 | $5,633,441 |
| Cook Islands |  | $294,940 |  | $0 | $115,713 |
| Fiji |  | $0 |  | $3,544,500 | $8,248,851 |
| Grenada |  | $0 |  | $0 | $535,000 |
| India |  | $3,385,204 |  | $1,100,000 | $1,501,007 |
| Indonesia |  | $2,770,580 |  | $41,163,559 | $92,371,647 |
| Kiribati |  | $0 |  | $2,295,073 | $2,900,322 |
| Lao People's Democratic Republic |  | $0 |  | $243,802 | $7,876,067 |
| Malaysia |  | $0 |  | $0 | $54,659 |
| Maldives |  | $0 |  | $0 | $1,529,374 |
| Marshall Islands |  | $0 |  | $0 | $202,192 |
| Micronesia, Federated States of |  | $0 |  | $0 | $933,957 |
| Mongolia |  | $0 |  | $0 | $1,024,571 |
| Mozambique |  | $0 |  | $0 | $145,118 |
| Myanmar |  | $0 |  | $2,962,600 | $0 |
| Nauru |  | $0 |  | $1,454,369 | $764,477 |
| Nepal |  | $0 |  | $745,224 | $1,001,639 |
| Niue |  | $0 |  | $0 | $216,864 |
| Pakistan |  | $0 |  | $397,940 | $1,291,297 |
| Palau |  | $0 |  | $0 | $206,504 |
| Papua New Guinea |  | $144,366 |  | $52,932,970 | $50,864,184 |
| Philippines |  | $327,938 |  | $1,851,223 | $22,185,791 |
| Samoa |  | $0 |  | $1,221,599 | $5,296,578 |
| Solomon Islands |  | $0 |  | $12,960,214 | $2,132,486 |
| South Africa |  | $0 |  | $0 | $805 |
| Sri Lanka |  | $758,441 |  | $862,297 | $717,869 |
| Thailand |  | $3,624 |  | $403,840 | $120,663 |
| Timor-Leste |  | $3,178,749 |  | $1,972,231 | $2,220,356 |
| Tokelau |  | $0 |  | $0 | $151,462 |
| Tonga |  | $2,255,928 |  | $663,118 | $1,302,807 |
| Tuvalu |  | $0 |  | $0 | $758,382 |
| Uganda |  | $0 |  | $4,199 | $0 |
| Vanuatu |  | $0 |  | $1,609,050 | $8,328,379 |
| Viet Nam |  | $15,831,560 |  | $1,430,647 | $18,318,923 |
| Far East Asia Unspecified |  | $526,758 |  | $9,641,341 | $282,488 |
| Global Unspecified** |  | $13,404,735 |  | $77,928,727 | $16,686,511 |
| Oceania Unspecified |  | $70,843 |  | $20,664,196 | $6,091,151 |
| South & Central Asia Unspecified |  | -$167,227 |  | $3,131,077 | $0 |
| South of Sahara Unspecified |  | $0 |  | $6,226,683 | $8,366,686 |
| Grand Total |  | $46,468,333 |  | $262,926,551 | $279,418,688 |
| *Provisional figures |  |  |  |  |  |
| **Includes payments to Multilateral Organisations |  |  |  | Source: AusAID Statistical Databases |  |

| Question 26: Attachment D |  |  |
| --- | --- | --- |
| Other Government Department Expenditure—2005–06 Expected Outcome |  |  |
| Department |  | 2005-06 Expected Outcome $m |
| Agriculture Fisheries and Forestry |  | 7,178,085 |
| Attorney-Generals |  | 155,398,524 |
| Australian Bureau of Statistics |  | 10,000 |
| Communications Information Technology and the Arts |  | 6,206,045 |
| Customs |  | 2,500,000 |
| Defence |  | 33,970,310 |
| Education Science and Training |  | 1,931,325 |
| Employment Workplace Relations and Small Business |  | 927,974 |
| Environment and Heritage |  | 5,173,459 |
| Foreign Affairs and Trade |  | 352,760,510 |
| Health and Ageing |  | 10,248,752 |
| Immigration and Multicultural and Indigenous Affairs |  | 159,796,872 |
| Industry Tourism and Resources |  | 334,296 |
| Reserve Bank of Australia |  | 12,500 |
| Treasury |  | 2,766,495 |
| ACT Government |  | 30,500 |
| Northern Territory Government |  | 23,500 |
| Queensland Government |  | 4,905,249 |
| Tasmanian Government |  | 584,939 |
| Victorian Government | 9,903,102 |  |
| Western Australian Government | 66,292 |  |
| Grand Total | 754,728,729 |  |

|  |  |  |  |  |  | Question 89: Attachment E |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AUSAID ODA ELIGIBLE EXPENDITURE ON COUNTER–TERRORISM1 IN THE LAST THREE FINANCIAL YEARS |  |  |  |  |  |  |  |  |  |
| Countries | Implementing Agency/ Contractor | Other sub-contractors or consultants | Public servants engaged in the project2 | Activity | Expend. 2003/04 $000 | Expend. 2004/05 $000 | Expend. 2005/06 $000 | Total Funding 2003- 06 $000 |  |
| AusAID-funded counter-terrorism projects and programs |  |  |  |  |  |  |  |  |  |
| APEC (Philippines, Thailand, Vietnam, PNG and Indonesia) | DOTARS | N/A | N/A | Assistance in Implementation of IMO Maritime Security Measures | 203 | 0 | 0 | 203 |  |
| APEC (China, Indonesia, Thailand, PNG, Philippines, Vietnam, Malaysia) | DFAT | N/A | N/A | Case studies in the implementation of APEC's Secure Trade Agenda | 94 | 0 | 0 | 94 |  |
| APEC (held in Singapore) | DOTARS | N/A | N/A | APEC Maritime and Port Security Capacity Building | 0 | 0 | 110 | 110 |  |
| APEC (held in Manila; Vietnam and PNG representatives) | DFAT with DSTO (Defence) | N/A | N/A | MANPADS Vulnerability Assessment Methodology Seminar | 0 | 0 | 6 | 6 |  |
| Asia/Pacific Regional | AGD | N/A | N/A | Asia Pacific Group on Money Laundering | 36 | 50 | 661 | 747 |  |
| Multi-Country (Cambodia, China, Fiji, Indonesia, Pakistan, Philippines, Vietnam) | University of Wollongong's Centre for Transnational Crime Prevention | N/A | N/A | Scholarships | 0 | 0 | 385 | 385 |  |
| Asia Regional (Thailand, Burma, Brunei, Indonesia, Philippines, Singapore, Cambodia, Vietnam, Malaysia, Lao PDR) | ACIL Pty Ltd The Distillery University of Wollongong | N/A | N/A | Basic Course for Senior Officials in CT Recognition and Multilateral Collaboration for combating terrorism | 480 | 0 | 0 | 480 |  |
| Asia Regional (ADB member countries and APEC economies) | ADB | N/A | N/A | Cooperation Fund for Regional Trade and Financial Security Initiative | 1,000 | 250 | 250 | 1,500 |  |
| Cambodia | AGD | N/A | N/A | Draft counter-terrorism legislation and support for enactment | 0 | 0 | 125 | 125 |  |
| Fiji (suspended Dec 2006) | AUSTRAC | Red Hat Training Ltd; Datec Fiji Ltd. | N/A | Fiji financial intelligence unit financial management system online | 0 | 0 | 227 | 227 |  |
| Indonesia | AUSTRAC/ other | Octavius Tjiantoro, Usmanto Njo, Gavin Forte. | N/A | Counter-terrorism Capacity Building Initiative - Terrorist Financing | 370 | 290 | 32 | 692 |  |
| Indonesia | AFP | Indonesia Australia Language Foundation; Canberra Institute of Technology. | N/A | Indonesia Counter-terrorism Forensic Capacity Building Program - Forensic Scholarship for 2 INP Forensic Specialists to undertake Certificate/Diploma | 220 | 0 | 0 | 220 |  |
| Indonesia | AFP | Peter Kelly, Geoff Forrester Asia & Associates; John Ireland; Glenn Crannage, Global Justice Solutions; Courage Partners Pty Ltd (Crisis Management Workshop); Jean Gordon (D). | N/A | Counter-terrorism Capacity Building Initiative - AFP-POLRI | 753 | 1,163 | 977 | 2,893 |  |
| Indonesia | Customs | N/A | N/A | Counter-terrorism Capacity Building Initiative - Special Travel Security Fund - Indonesia - Australia Customs Maritime Security Capacity Building Project | 0 | 708 | 0 | 708 |  |
| Indonesia | DIAC | CPS Systems | N/A | Counter-terrorism Capacity Building Initiative - Special Travel Security Fund - Border Management Alert System | 0 | 115 | 1,097 | 1,212 |  |
| Indonesia | DOTARS | Peter Dunn; Peter McLinton; Trevor Joy; Lin Sinton; Bob Adams. | N/A | Counter-terrorism Capacity Building Initiative - Special Travel Security Fund - Indonesia Aviation Security Project | 0 | 486 | 682 | 1,168 |  |
| Pacific Regional (Cook Islands, Nauru, Palau, PNG, Samoa, Solomon Islands, Tonga, Vanuatu) | AUSTRAC | N/A | N/A | Pacific Islands' Financial Intelligence Unit Database Project | 0 | 242 | 0 | 242 |  |
| Pacific Regional (Cook Islands) | AUSTRAC | N/A | N/A | Cook Islands leadership of Oceania representation within the Egmont group of financial intelligence units | 0 | 0 | 73 | 73 |  |
| Pacific Regional | DFAT | N/A | N/A | Ready Pasifika | 0 | 0 | 121 | 121 |  |
| Pacific Regional (SPC membership countries) | DOTARS | N/A | N/A | Enhancing Aviation and Maritime Security in the Pacific (Phase I) | 0 | 646 | 0 | 646 |  |
| Pacific Regional (SPC membership countries) | DOTARS | N/A | N/A | Enhancing Aviation and Maritime Security in the Pacific (Phase II) | 0 | 0 | 222 | 222 |  |
| Pacific Regional (Cook Islands, Fiji, FSM, Kiribati, Marshalls, Nauru, Niue, Palau, Samoa, Solomons, Tuvalu, Tonga, Vanuatu) | SPC | Asia Pacific Maritime Institute (Australia), NZ Maritime School (NZ), PNG Maritime College (PNG). | N/A | Security in the Pacific Islands Maritime Sector (Phase I) | 0 | 311 | 0 | 311 |  |
| Pacific Regional (Cook Islands, Fiji, FSM, Kiribati, Marshalls, Nauru, Niue, Palau, Samoa, Solomons, Tuvalu, Tonga, Vanuatu) | SPC | Asia Pacific Maritime Institute (Aust); NZ Maritime School; PNG Maritime College; Optimum Marine (NZ); University of Wollongong (Aust). | N/A | Maritime Security in the Pacific (Phase II) | 0 | 1,054 | 1,029 | 2,083 |  |
| Papua New Guinea | DOTARS | N/A | Col Kuchel (Deputy CEO Civil Aviation Authority), Andrew Scottney-Turbill (Aviation Security) and Phil Price (Maritime Security). | Enhanced Cooperation Program Maritime Security | 0 | 355 | 642 | 997 |  |
| Philippines | AFP | Jean Gordon (D) Charles Sturt University; Global Justice Solutions; APIS Consulting Group. | N/A | Counter-terrorism Capacity Building Initiative - Philippines Law Enforcement | 1,056 | 1,293 | 815 | 3,164 |  |
| Philippines | DIAC | N/A | N/A | Border Control - Document Examination Laboratory | 87 | 72 | 0 | 159 |  |
| Philippines | DOTARS | Bill Pennington, Eileen Wahab (D) Intelligent Outcomes Group, Sustainable Development Solutions | N/A | Port Security | 0 | 987 | 996 | 1,983 |  |
| Philippines | Mindanao Economic Development Council | National Democratic Institute, Davao Chamber of Commerce, Gerry Roxas Foundation, & individual contractors in Philippines. | N/A | Strengthening the BIMP-EAGA Support Team on Customs, Immigration, Quarantine and Security | 0 | 0 | 247 | 247 |  |
| Philippines, Indonesia, Malaysia, Brunei | Philippine CIQS agencies | N/A | N/A | Regional Cooperation | 28 | 0 | 0 | 28 |  |
| Philippines, Thailand, Vietnam, PNG and Indonesia | DOTARS Customs | N/A | N/A | APEC Support Program: Assistance on the implementation of international maritime security measures and associated institutional arrangements | 250 | 0 | 0 | 250 |  |
| GRAND TOTAL |  |  |  |  | $4,577 | $8,021 | $8,697 | $21,295 |  |
| Notes: |  |  |  |  |  |  |  |  |  |
| 1. Includes activities with specific components aimed at building counter-terrorism capacity. Figures do not include broader law and justice, and governance programs. |  |  |  |  |  |  |  |  |  |
| 2. Not including those employed in normal public servant roles by the implementing Australian government department, by AusAID as the funding agency, or by partner governments (ie local employees). |  |  |  |  |  |  |  |  |  |
| 3. (D) Design consultant |  |  |  |  |  |  |  |  |  |
| 4. N/A Not applicable |  |  |  |  |  |  |  |  |  |
| Abbreviations |  |  |  |  |  |  |  |  |  |
| ADB | Asian Development Bank |  |  |  |  |  |  |  |  |
| AFP | Australian Federal Police |  |  |  |  |  |  |  |  |
| AGD | Attorney General's Department |  |  |  |  |  |  |  |  |
| APEC | Asia Pacific Economic Cooperation |  |  |  |  |  |  |  |  |
| AUSTRAC | Australian Transaction Reports and Analysis Centre |  |  |  |  |  |  |  |  |
| BIMP-EAGA | Brunei Indonesia Malaysia Philippines - East ASEAN Growth Area |  |  |  |  |  |  |  |  |
| CIQS | Customs Immigration Quarantine and Security |  |  |  |  |  |  |  |  |
| CT | Counter-terrorism |  |  |  |  |  |  |  |  |
| Customs | Australian Customs Service |  |  |  |  |  |  |  |  |
| DFAT | Department of Foreign Affairs and Trade |  |  |  |  |  |  |  |  |
| DIAC | Department of Immigration and Citizenship |  |  |  |  |  |  |  |  |
| DOTARS | Department of Transport and Regional Services |  |  |  |  |  |  |  |  |
| DSTO | Defence Science and Technology Organisation |  |  |  |  |  |  |  |  |
| FSM | Federated States of Micronesia |  |  |  |  |  |  |  |  |
| IMF | International Monetary Fund |  |  |  |  |  |  |  |  |
| IMO | International Maritime Organisation |  |  |  |  |  |  |  |  |
| INP | Indonesian National Police |  |  |  |  |  |  |  |  |
| MANPADS | Man Portable Air Defence Systems |  |  |  |  |  |  |  |  |
| POLRI | Indonesian National Police |  |  |  |  |  |  |  |  |
| SPC | Secretariat of the Pacific Community |  |  |  |  |  |  |  |  |
| UNDP | United National Development Program |  |  |  |  |  |  |  |  |

Question 103: Attachment F

Question 103: Attachment G

Question 103: Attachment H