# PART II

## The Tendering Process and Contract

In this section of the Report, the Committee turns to the issues of the tendering process and the contract.

In Chapter Six, the Committee inquires into the process leading up to the signing of a contract in June 2000 with INVAP of Argentina for the construction of a new nuclear reactor at Lucas Heights.

In Chapter Seven, the Committee examines the nature of the contractual commitments entered into.

## REPLACEMENT RESEARCH REACTOR PROJECT CHRONOLOGY

| Milestones | Date |
| --- | --- |
| Government Decision | 3 September 1997 |
| ANSTO seeks expressions of interest | July 1998 |
| Pre-qualification - Pre-qualification briefing (September 1998) - Formal pre-qualification request close (November 1998) - Pre-qualification meetings with six vendors (November–December 1998) - Selection of pre-qualified reactor vendors (December 1998) | September 1998 |
| Formation of Request for Tender Team | January 1999 |
| Site visit to Reference reactors | April 1999 |
| Issue of draft Principal’s Project Requirements | April 1999 |
| Red Team Review | June 1999 |
| Request for Tender Issued - Joint tenderer briefing (6 September 1999) - Geotechnical investigation of site (September–October 1999) - Mid term tender preparation review meeting (September–October 1999) - Tenders close (December 1999) | 28 August 1999 |
| Tenders opened - Tender briefings (6–7 January) - Initial compliance check (8 January) - Detailed evaluation (10 January–27 February) - Clarification meetings (6 March–1 April) - Submission of Supplementary Pricing Proposals - Detailed financial analysis (April) - Completion of Team Leader Report (April) - Comparative Review by Tender Evaluation Management Group (2–4 May 2000) - Tender Selection Review Committee (10 May–13 May 2000) Tender evaluation completed with final recommendation. | 3 January 2000 |
| Government announced successful tenderer—INVAP | 6 June 2000 |
| Contract signed for replacement research reactor | 13 July 2000 |
| Government announce search for a site for the national store for intermediate level radioactive waste | 11 August 2000 |
| Detailed design including systems requirement reviews and system critical design reviews. | July 2000–May 2002 |
| Construction authorisation by ARPANSA including preliminary safety analysis report | April 2002 |
| Construction commencement | May 2002 |
| Low power Reactor Commissioning | March 2005 |
| High power Reactor Commissioning | June 2005 |
| Operation Authorisation by ARPANSA including Final Safety Report | September 2005 |
| Replacement Reactor Full Operations | December 2005 |
| Permanent Shutdown of HIFAR | December 2005 |

Taken from Parliamentary Standing Committee on Public Works, Proposed Replacement Nuclear Research Reactor, Lucas Heights, NSW, 12 August 1999, p. 124 and ANSTO, submission no. 118, Attachment G.

Professor Garnett stated that detailed design drawings that form part of the development of the safety assessment to go for a construction licence will be completed by the first half of 2001. Committee Hansard, 9 October 2000, p. 16.